## Agile Project Plan (hidden)
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Downhill | Tommy Andrews | 2021-01-13 | 2021-04-20 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Tommy Andrews | 16 | 2021-01-14 | 2021-02-03 | 22 | Completed | During the sprint 1 the priority was given to planning and documentation. Two basic features were selected to be implemented, but will be enhaced during sprint 2
| Authentication and User Management | Authentication | Juan Sebastian Hoyos | 8 | 2021-01-25 | 2021-02-04 | 11 | Completed | The Main functionnalty of authentication will be implemented and some small parts of user management will carry over sprint 2
| Adding inventory stock | Logistics | Shahid Khan | 8 | 2021-01-20 | 2021-04-02 | 16 | Completed | This feature is a very big feature therefore it was split into two small epics but the main epic spans over sprint 1 and sprint 2
| Sprint 2 |  | Ashwin Philip | 24 | 2021-03-03 | 2021-02-24 | 22 | In Progress | Sprint 2 will be a high load in the development of the main features. During this sprint the enhacement of the inventory feature will be done as well as the addition of two complete new features.
| Net Income Graph Generation | Accounting | Kevin Marsolais | 8 | 2021-03-17 | 2021-03-24 | 15 | In Progress | Accountants can generate a graph of the net income of the company calculated from the "accounts payable" and the "accounts receivable".
| Accounts Payable/Receivable | Accounting | Tommy Andrews | 10 | 2021-03-03 | 2021-03-17 | 15 | In Progress | All the purchases, sales, and refunds will be displayed in a list that only accountants will have permission to access. Accountants have the ability to approve new stock purchase or decline it.
| Inventory Management | Logistics | Noah Freger | 1 | 2021-03-03 | 2021-03-03 | 22 | In Progress | Inventory manamenet employees will be able to modify the inventory by adding new inventory, or removing inventory. All employees will be able to see the available inventory at the moment
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt